## Sheet1
BLDG. GANTT CHART
| Group | BLDG. |  | Department |  | Computer Engineering
| Semester | 2nd Semester |  | SY |  | 2025-2026
ID | TASK | START DATE | END DATE |  | STATUS |  | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | [6 empty] | WEEK 7 | [6 empty] | WEEK 8 | [5 empty] | WEEK 9 | [6 empty] | WEEK 10 | [6 empty] | WEEK 11 | [7 empty] | WEEK 12 | [6 empty] | WEEK 13 | [6 empty] | WEEK 14 | [6 empty] | WEEK 15 | [6 empty] | WEEK 16 | [6 empty] | WEEK 17 | [6 empty] | WEEK 18
[7 empty] | 11 / 29 | 11 / 30 | 12 / 01 | 12 / 02 | 12 / 03 | 12 / 04 | 12 / 05 | 12 / 06 | 12 / 07 | 12/ 08 | 12 / 09 | 12 / 10 | 12 / 11 | 12 / 12 | 12 / 13 | 12 / 14 | 12 / 15 | 12 / 16 | 12 / 17 | 12 / 18 | 12 / 19 | 01 / 10 | 01 / 11 | 01 / 12 | 01 / 13 | 01 / 14 | 01 / 15 | 01 / 16 | 01 / 17 | 01 / 18 | 01 / 19 | 01 / 20 | 01 / 21 | 01 / 22 | 01 / 23 | 01 / 24 | 01 / 25 | 01 / 26 | 01 / 27 | 01 / 28 | 01 / 29 | 01 / 30 | 01 / 31 | 02 / 01 | 02 / 02 | 02 / 03 | 02 / 04 | 02 / 05 | 02 / 06 | 02 / 07 | 02 / 08 | 02 / 09 | 02 / 11 | 02 / 12 | 02 / 13 | 02 / 14 | 02 / 15 | 02 / 16 | 02 / 17 | 02 / 18 | 02 / 19 | 02 / 20 | 02 / 21 | 02 / 22 | 02 / 23 | 02 / 24 | 02 / 25 | 02 / 26 | 02 / 27 | 02 / 28 | 02 / 29 | 03 / 01 | 03 / 02 | 03 / 03 | 03 / 04 | 03 / 05 | 03 / 06 | 03 / 07 | 03 / 08 | 03 / 09 | 03 / 10 | 03 / 11 | 03 / 12 | 03 / 13 | 03 / 14 | 03 / 15 | 03 / 16 | 03 / 17 | 03 / 18 | 03 / 19 | 03 / 20 | 03 / 21 | 03 / 22 | 03 / 23 | 03 / 24 | 03 / 25 | 03 / 26 | 03 / 27 | 03 / 28 | 03 / 29 | 03 / 30 | 03 / 31 | 2026-04-01 | 2026-04-02 | 2026-04-03 | 2026-04-04 | 2026-04-05 | 2026-04-06 | 2026-04-07 | 2026-04-08 | 2026-04-09 | 2026-04-10 | 2026-04-11 | 2026-04-12 | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-16 | 2026-04-17 | 2026-04-18 | 2026-04-19 | 2026-04-20
1 | PLANNING PHASE | bar: WEEK 3 12 / 15 to WEEK 18 2026-04-20
1.1 | Brainstorming | 2025-11-29 | 2025-11-29 |  | Done | bar: WEEK 1 11 / 29
1.2 | Researching | 2025-11-29 | 2025-11-30 |  | Done | bar: WEEK 1 11 / 29 to WEEK 1 11 / 30
1.3 | Conceptualization | 2025-11-29 | 2025-12-06 |  | Done | bar: WEEK 1 11 / 29 to WEEK 2 12 / 06
1.4 | Searching for Possible client | 2025-11-29 | 2025-12-08 |  | Done | bar: WEEK 1 11 / 29 to WEEK 2 12/ 08
1.5 | Background checking of the possible client | 2025-11-29 | 2025-12-10 |  | Done | bar: WEEK 1 11 / 29 to WEEK 2 12 / 10
2 | REQUIREMENTS | bar: WEEK 3 12 / 15 to WEEK 18 2026-04-20
2.1 | Making of interview questions. | 2025-12-13 | 2025-12-13 |  | Done | bar: WEEK 3 12 / 13
2.2 | Selecting of the Client | 2025-12-06 | 2025-12-08 |  | Done | bar: WEEK 2 12 / 06 to WEEK 2 12/ 08
2.3 | Interviewing the Client | 2025-12-14 | 2025-12-14 |  | Done | bar: WEEK 3 12 / 14
2.4 | Analyzing and interpreting the data | 2025-12-15 | 2025-12-19 |  | Done | bar: WEEK 3 12 / 15 to WEEK 3 12 / 19
3 | bar: WEEK 3 12 / 15 to WEEK 18 2026-04-20
3.1 | Algorithm | 2026-01-10 | 2026-01-24 |  | Done | bar: WEEK 4 01 / 10 to WEEK 6 01 / 24
3.2 | Flowchart | 2026-01-24 | 2026-01-28 |  | Done | bar: WEEK 6 01 / 24 to WEEK 6 01 / 28
3.3 | DFD (Data Flow Diagram) | 2026-01-17 | 2026-02-02 |  | Done | bar: WEEK 5 01 / 17 to WEEK 7 02 / 02
3.4 | ERD (Entity-Relationship Diagram) | 2026-01-10 | 2026-02-19 |  | Done | bar: WEEK 4 01 / 10 to WEEK 9 02 / 19
3.5 | Storyboarding | 2025-12-06 | 2025-12-19 |  | Done | bar: WEEK 2 12 / 06 to WEEK 3 12 / 19
4 | DEVELOPMENT PHASE | bar: WEEK 3 12 / 15 to WEEK 18 2026-04-20
4.1 | Front-End Development | 2026-01-24 | 2026-03-01 |  | Done | bar: WEEK 6 01 / 24 to WEEK 11 03 / 01
4.2 | Back-End Development | 2026-01-31 | 2026-03-15 |  | Done | bar: WEEK 7 01 / 31 to WEEK 13 03 / 15
4.3 | Database Management System | 2026-01-31 | 2026-03-15 |  | Done | bar: WEEK 7 01 / 31 to WEEK 13 03 / 15
4.4 | System Testing | 2026-03-16 | 2026-03-23 |  | Done | bar: WEEK 13 03 / 16 to WEEK 14 03 / 23
4.5 | Debugging | 2026-03-24 | 2026-03-31 |  | Done | bar: WEEK 14 03 / 24 to WEEK 15 03 / 31
5 | QA & TESTING | bar: WEEK 3 12 / 15 to WEEK 18 2026-04-20
5.1 | Multiple Device Test | 2026-04-01 | 2026-04-03 |  | Done | bar: WEEK 15 2026-04-01 to WEEK 15 2026-04-03
5.2 | Beta Testing | 2026-04-04 | 2026-04-07 |  | Done | bar: WEEK 16 2026-04-04 to WEEK 16 2026-04-07
6 | DEPLOYMENT & MAINTENANCE | bar: WEEK 3 12 / 15 to WEEK 18 2026-04-20
6.1 | Authoring Privacy Policies and User Manual | 2026-04-01 | 2026-04-07 |  | Done | bar: WEEK 15 2026-04-01 to WEEK 16 2026-04-07
6.2 | Deployment | 2026-04-08 | 2026-04-09 |  | Done | bar: WEEK 16 2026-04-08 to WEEK 16 2026-04-09
6.3 | Maintenance | 2026-04-10 | 2026-04-16 |  | Done | bar: WEEK 16 2026-04-10 to WEEK 17 2026-04-16
7 | DOCUMENTATION
7.1 | Chapter 1 : The Project And It's Background | 2025-12-19 | 2026-01-24 |  | Done | bar: WEEK 3 12 / 19 to WEEK 6 01 / 24
7.2 | Chapter 2 : Software Design | 2026-01-24 | 2026-02-20 |  | Done | bar: WEEK 6 01 / 24 to WEEK 9 02 / 20
7.3 | Chapter 3 : Design Tradeoffs | 2026-02-21 | 2026-03-15 |  | Done | bar: WEEK 10 02 / 21 to WEEK 13 03 / 15
7.4 | Chapter 4 : Final Design | 2026-03-16 | 2026-04-07 |  | Done | bar: WEEK 13 03 / 16 to WEEK 16 2026-04-07
7.5 | Chapter 5 : Business Plan and Model | 2026-04-08 | 2026-04-12 |  | Done | bar: WEEK 16 2026-04-08 to WEEK 17 2026-04-12
7.6 | Final Paper Check | 2026-04-13 | 2026-04-17 |  | Done | bar: WEEK 17 2026-04-13 to WEEK 17 2026-04-16
7.7 | Defense | 2026-04-20 | 2026-04-20 |  | Done | bar: WEEK 18 2026-04-20